## Marketing Team Goals
Month | Goal Type | Team Member | Goal Description | Status
June 2024 | Team | Marketing Team | Increase overall brand visibility by 20% through digital campaigns | In Progress
June 2024 | Individual | Ishita Sharma | Execute 3 influencer campaigns for Instagram | Completed
June 2024 | Individual | Raghav Verma | Publish 8 SEO blog articles on product use-cases | In Progress
June 2024 | Individual | Ananya Pillai | Generate 500 qualified leads through paid ads | Not Started
June 2024 | Individual | Kunal Mehta | Create YouTube series: 'Behind the Brand' | In Progress
June 2024 | Individual | Sneha Iyer | Optimize 10 product pages for conversion | Completed
June 2024 | Team | Marketing Team | Boost LinkedIn engagement by 30% | Not Started
June 2024 | Individual | Kunal Mehta | Develop competitor benchmarking report | Completed
June 2024 | Individual | Sneha Iyer | Design ad creatives for upcoming monsoon campaign | In Progress
June 2024 | Individual | Ishita Sharma | Launch a WhatsApp broadcast campaign for new users | Pending

## Project Tracking
Task ID | Team Member | Project | Task | Deadline | Status
301 | Ishita Sharma | Instagram Campaigns | Identify and onboard 5 regional influencers | 2024-06-10 | Completed
302 | Raghav Verma | Content Strategy | Draft blog structure for product benefits | 2024-06-11 | Completed
303 | Ananya Pillai | Lead Generation | Design landing pages for ads | 2024-06-12 | In Progress
304 | Raghav Verma | Blog SEO Optimization | Integrate keyword tracking tools | 2024-06-13 | Pending
305 | Ishita Sharma | Influencer Outreach | Negotiate terms with influencer partners | 2024-06-14 | Not Started
306 | Kunal Mehta | YouTube Series | Script and shoot intro episode | 2024-06-15 | In Progress
307 | Sneha Iyer | Product Page Optimization | Rewrite product copy for top-selling items | 2024-06-16 | Completed
308 | Kunal Mehta | Competitor Research | Collect data on top 5 competitors | 2024-06-17 | Completed
309 | Sneha Iyer | Monsoon Campaign | Design monsoon-themed visual creatives | 2024-06-18 | In Progress
310 | Ishita Sharma | WhatsApp Campaign | Segment WhatsApp user base | 2024-06-19 | Pending
311 | Ananya Pillai | Lead Funnel A/B Test | Create landing pages for lead capture | 2024-06-20 | Completed
312 | Raghav Verma | SEO Internal Linking | Add internal links across all articles | 2024-06-21 | Pending
313 | Kunal Mehta | YouTube Analytics | Analyze watch time and bounce rates | 2024-06-22 | In Progress
314 | Sneha Iyer | Ad Copy Testing | Test ad variants across platforms | 2024-06-23 | In Progress
315 | Ananya Pillai | Paid Ads Monitoring | Set up weekly ad performance dashboard | 2024-06-24 | Pending
316 | Sneha Iyer | Customer Retargeting | Build audience list for retargeting | 2024-06-25 | Completed
317 | Kunal Mehta | Brand Positioning Survey | Prepare survey questions and test logic | 2024-06-26 | Pending
318 | Raghav Verma | Email Automation | Integrate email workflow in CRM | 2024-06-27 | In Progress
319 | Ishita Sharma | Instagram Analytics | Pull engagement metrics from last 30 days | 2024-06-28 | Completed
320 | Sneha Iyer | Campaign Reporting | Compile weekly report with KPIs | 2024-06-29 | Pending

## Risks & Issues
Reported Date | Team Member | Issue Title | Description | Severity | Mitigation Plan | Status
2024-06-08 | Ananya Pillai | Low CTR on paid ads | Click-through rates on paid ad campaigns are below 1.2%, which is lower than industry average. | High | A/B test different creatives and revise ad targeting parameters. | Open
2024-06-14 | Raghav Verma | SEO tools access delay | Waiting for IT team to enable access to SEMrush and Ahrefs for ongoing blog optimizations. | Medium | Follow up with IT and use free tool alternatives temporarily. | Resolved
2024-06-16 | Kunal Mehta | Video editing tool crashes | Adobe Premiere Pro crashing repeatedly while rendering video for YouTube. | High | Switch to alternative editing software and reduce render size. | Open
2024-06-18 | Sneha Iyer | Delayed asset delivery from design | Creative team delayed in sending assets for monsoon campaign launch. | Medium | Use placeholder creatives temporarily and adjust launch timeline. | In Progress
2024-06-20 | Ishita Sharma | WhatsApp campaign approval stuck | WhatsApp campaign template still awaiting approval from business manager. | High | Escalate to Meta support and prepare alternate channel plan. | Open
2024-06-22 | Raghav Verma | Email bounce rates unexpectedly high | Initial emails sent to user list resulted in 15%+ bounce rate. | High | Clean email list, run deliverability tests, and resend to verified users. | Investigating